## Status
Project Status Report
Edit the blue cells. The status flag and rollups recalculate on their own.
Field | Value
Project | [Project name]
Prepared by | [Your name / company]
Client | [Client name]
Reporting period | [Start] – [End]
Overall status
Summary | [Two or three sentences a stakeholder can forward]
Live rollup (auto)
% complete (project)
Milestones done
Milestones due soon
Milestones late
Milestones total

## Milestones
Milestone | Owner | Due date | % complete | Status
Discovery & kickoff | Alex | 2026-05-20 | 100%
Design mockups | Sam | 2026-06-08 | 60%
Frontend build | Jordan | 2026-06-12 | 30%
QA & launch | Sam | 2026-06-30 | 0%
Formulas:
Status = IF([Due date]="","",IF(D2>=1,"🟢 Done",IF([Due date]<TODAY(),"🔴 Late",IF([Due date]-TODAY()<=3,"🟡 Due soon","🟢 On track"))))

## Risks
Risk / issue | Impact | Owner | Next action | Status
Client assets delayed | High | Alex | Chase final logo + copy | Open
Scope creep on dashboard | Med | Sam | Confirm scope in writing | Open